## MAR 11
Rosen College Career Fair Spring 2025
Name | Department | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00
Steven Brinkman | CEO | CLASS |  |  | AVAILABLE
Kaitlin Smith | Event Lead | CLASS |  |  | AVAILABLE
Harley Paul | Event Co-Lead | CLASS |  |  | AVAILABLE
Drake Speno | Marketing Lead | CLASS |  |  | AVAILABLE
Merelin Almonte | Marketing Co-Lead | CLASS | [10 empty] | AVAILABLE
Cate Daugherty | Marketing | CLASS |  |  | AVAILABLE
Amy Helgeson | Marketing | CLASS
Kiley McDermott | Marketing | CLASS
Dania Maria Alvarado Soler | Marketing | CLASS | [15 empty] | AVAILABLE
Alexis Jones | Decor/F&B Lead | CLASS |  |  | OVERLOOK PRE-SET UP/CATEGORIZE DECOR | [5 empty] | DINING ROOM SET UP
Bianka Mejia | Decor/F&B Co-Lead | CLASS |  |  | OVERLOOK PRE-SET UP/CATEGORIZE DECOR | [5 empty] | DINING ROOM SET UP
Adam Holbrook | Decor/F&B | CLASS |  |  | SET UP READY/RELAXATION ROOM | [6 empty] | DINING ROOM/RELAXATION ROOM SET UP
Emily Strickland | Decor/F&B | CLASS |  |  | AVAILABLE
Tamara Hofinger | Decor/F&B | CLASS |  |  | ORGANIZE DECOR FOR DINING ROOM
Ashlyn Straughn | Decor/F&B | CLASS |  |  | ORGANIZE DECOR FOR DINING ROOM | [9 empty] | DINING ROOM SET UP
Isabela Irizarry | Operations Lead | CLASS |  |  | FINAL BADGE PRINTING/ORGANIZING | [7 empty] | MOVE SUPPLIES TO EVENT CLOSET |  |  | AVAILABLE
Justina Ruiz | Operations Co-Lead | CLASS |  |  | FINAL BADGE PRINTING/ORGANIZING | [7 empty] | MOVE SUPPLIES TO EVENT CLOSET |  |  | AVAILABLE
Hayden Harper | Operations | CLASS |  |  | FINAL BADGE PRINTING/AVAILABLE
Mia Husty | Operations | CLASS |  |  | FINAL BADGE PRINTING/ORGANIZING/AVAILABLE | [7 empty] | MOVE SUPPLIES TO EVENT CLOSET |  |  | AVAILABLE
Lily Hong | Operations | CLASS |  |  | FINAL BADGE PRINTING/ORGANIZING/AVAILABLE
Hayeon Kim | Operations | CLASS
Deja-Ray Mason | Training/Development Lead | CLASS | [15 empty] | AVAILABLE
Logan Lyon | Training/Development Co-Lead | CLASS |  |  | ORGANIZE GIFTS/GET STUFF OUT OF CLOSET | [5 empty] | AVAILABLE
Sera Singleton | Training/Development | CLASS |  |  | AVAILABLE
Elliana Ortiz | Training/Development | CLASS
Amelia Patane | Training Development | CLASS |  |  | AVAILABLE
Alex Trevino | Sales/Development Lead | CLASS | [12 empty] | AVAILABLE
Lauren Muermann | Sales Development Co-Lead | CLASS |  |  | AVAILABLE |  |  | CLASS |  |  | AVAILABLE
Olivia Townsend | Procurement Lead | CLASS |  |  | AVAILABLE/CLOSET MANAGEMENT
JoHannah Sill | Procurement Co-Lead | CLASS |  |  | AVAILABLE/CLOSET MANAGEMENT

## MAR 12
Rosen College Career Fair Spring 2025
Name | Department | 5:00 | 5:10 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00
Steven Brinkman | CEO | ARRIVE + CHECK IN | OVERSEE SET UP |  |  |  |  | WALKTHROUGH WITH FREEMAN |  | OVERSEE/FLOAT |  |  | OPENING CEREMONY | FIRE MARSHALL VISIT | OVERSEE/FLOAT | [5 empty] | CLASS PHOTO AND LUNCH BREAK |  | ASSIST WITH BREAKDOWN |  | FINISHED
Kaitlin Smith | Event Lead
Harley Paul | Event Co-Lead
Drake Speno | Marketing Lead | ARRIVE + CHECK IN | ASSIST WITH SETUP | [6 empty] | FILM PRE-EVENT REELS | FLOAT/CORDINATE CONTENT/ASSIST KNIGHTRO |  | OPENING CEREMONY | FILM/TAKE CONTENT | CAREER FAIR LEGACY WALL | SOCIAL MEDIA | BREAK/ MEET W/ EMPLOYERS |  | FILM/TAKE CONTENT | SOCIAL MEDIA |  |  | ASSIST W/ BREAKDOWN
Merelin Almonte | Marketing Co-Lead | [8 empty] | CONTINUE ASSISTING w/ SET UP | FLOAT/ASSIST STAFF |  | OPENING CEREMONY | CHECK IN W/ VOLUNTEERS | BREAK/ MEET W/ EMPLOYERS |  | SURVEY/COLLECT BADGES |  | SOCIAL MEDIA | SOCIAL MEDIA |  |  | ASSIST W/ BREAKDOWN
Cate Daugherty | Marketing | [8 empty] | FILM PRE-EVENT REELS | CORDINATE WITH STAFF |  | OPENING CEREMONY | CHECK IN W/ VOLUNTEERS | BREAK/ MEET W/ EMPLOYERS |  | SOCIAL MEDIA |  | CHECK IN ON PHOTO BOOTH | FILM VLOG |  |  | ASSIST W/ BREAKDOWN
Amy Helgeson | Marketing | [8 empty] | CONTINUE ASSISTING w/ SET UP | ASSIST WITH VOLUNTEERS |  | OPENING CEREMONY | TAKE PROFESSIONAL PHOTOS W/ CAMERA | CAREER FAIR LEGACY WALL | TAKE PROFESSIONAL PHOTOS W/ CAMERA | CHARGE CAMERA/SOCIAL MEDIA | CHECK IN ON PHOTO BOOTH | BREAK/ MEET W/ EMPLOYERS |  |  |  | ASSIST W/ BREAKDOWN
Kiley McDermott | Marketing | [8 empty] | FILM PRE-EVENT REELS | KNIGHTRO ATTENDANT |  | OPENING CEREMONY | FILM/TAKE CONTENT | CAREER FAIR LEGACY WALL | SURVEY/COLLECT BADGES | CHECK IN W/ VOLUNTEERS | SOCIAL MEDIA | BREAK/ MEET W/ EMPLOYERS |  |  |  | ASSIST W/ BREAKDOWN
Dania Maria Alvarado Soler | Marketing | [8 empty] | FILM PRE-EVENT REELS | ASSIST WITH VOLUNTEERS |  | OPENING CEREMONY | KNIGHTRO ATTENDANT | CAREER FAIR LEGACY WALL | FLM CONTENT | BREAK/ MEET W/ EMPLOYERS |  | CHECK IN W/ VOLUNTEERS | SURVEY/COLLECT BADGES |  |  | ASSIST W/ BREAKDOWN
Alexis Jones | Decor/F&B Lead | ARRIVE + CHECK IN | WORK ON FRONT ENTRANCE |  |  | ASSIST WITH BREAKFAST SET UP |  | SET UP REGISTRATION TABLES |  | ASSIST W/REGISTRATION |  | CHECK IN EMPLOYERS | OPENING CEREMONY | SURVEY/COLLECT BADGES |  | BREAK/ MEET W/ EMPLOYER |  | MONITOR R&R ROOM | FLOATING | FLOATING |  |  | ASSIST W/BREAKDOWN
Bianka Mejia | Decor/F&B Co-Lead |  | WORK ON FRONT ENTRANCE |  |  | ASSIST WITH BREAKFAST SET UP |  | SET UP PATIO |  | OVERSEE EMPLOYER USHERS |  | CHECK IN EMPLOYERS | OPENING CEREMONY | BREAK/ MEET W/ EMPLOYER |  | SURVEY/COLLECT BADGES | OVERSEE EMPLOYEE DINING | FLOATING | OVERSEE EMPLOYEE DINING | SURVEYS/COLLECTING BADGES |  |  | ASSIST W/BREAKDOWN
Adam Holbrook | Decor/F&B |  | WORK ON FRONT ENTRANCE |  |  | ASSIST WITH BREAKFAST SET UP |  |  | FINAL TOUCHES ON RELAXATION ROOM | SET UP DRINKING STATION/STAND BY | EMPLOYER USHER | CHECK IN EMPLOYERS | OPENING CEREMONY | BREAKDOWN BREAKFAST | BREAK/ MEET W/ EMPLOYER |  | OVERSEE EMPLOYEE DINING | SURVEY/COLLECT BADGES | MONITOR R&R ROOM | BREAKDOWN LUNCH |  |  | ASSIST W/BREAKDOWN
Emily Strickland | Decor/F&B |  | WORK ON FRONT ENTRANCE |  |  | ASSIST WITH BREAKFAST SET UP |  | SET UP GAZEBO & RESTROOMS |  | SET UP DRINKING STATION/STAND BY | EMPLOYER USHER | BREAKDOWN BREAKFAST | OPENING CEREMONY | BREAKDOWN BREAKFAST | SET UP LUNCH | FLOATING | BREAK/ MEET W/ EMPLOYER |  | SURVEYS/COLLECTING BADGES | BREAKDOWN LUNCH |  |  | ASSIST W/BREAKDOWN
Tamara Hofinger | Decor/F&B |  | WORK ON FRONT ENTRANCE |  |  | ASSIST WITH BREAKFAST SET UP |  | SET UP GAZEBO & RESTROOMS |  | SET UP DRINKING STATION/STAND BY | EMPLOYER USHER | BREAKDOWN BREAKFAST | OPENING CEREMONY | BREAKDOWN BREAKFAST | SET UP LUNCH | MONITOR R&R ROOM | SURVEY/COLLECT BADGES | FLOATING | SURVEY/COLLECT BADGES | BREAKDOWN LUNCH |  |  | ASSIST W/BREAKDOWN
Ashlyn Straughn | Decor/F&B |  | WORK ON FRONT ENTRANCE |  |  | ASSIST WITH BREAKFAST SET UP |  |  | HELP WITH RELAXATION ROOM | SET UP DRINKING STATION/STAND BY | EMPLOYER USHER | CHECK IN EMPLOYERS | OPENING CEREMONY | BREAKDOWN BREAKFAST | MONITOR R&R ROOM | SURVEY/COLLECT BADGES | OVERSEE EMPLOYEE DINING | BREAK/ MEET W/ EMPLOYER |  | SURVEYS/COLLECTING BADGES |  |  | ASSIST W/BREAKDOWN
Isabela Irizarry | Operations Lead | ARRIVE + CHECK IN | COLLECT BADGES | STUDENT REGISTRATION/BADGES |  | OVERSEE REGISTRATION/BADGES |  | FREEMAN WALKTHROUGH |  | FINALIZE STUDENT REGISTRATION | STUDENT REGISTRATION |  | OPENING CEREMONY | FIRE MARSHALL VISIT | BREAK/ MEET W/ EMPLOYER |  | OVERSEE REGISTRATION/FLOAT |  |  | OVERSEE/FLOAT |  |  | REGISTRATION BREAKDOWN
Justina Ruiz | Operations Co-Lead |  |  | OVERSEE LOAD-IN |  | EXHIB. REGISTRATION |  |  |  | FINALIZE STUDENT REGISTRATION | ON-SITE REGISTRATION/OVERSEE EXHIB. |  | OPENING CEREMONY | ON-SITE REGISTRATION |  | OVERSEE REGISTRATION | BREAK/ MEET W/ EMPLOYER |  | OVERSEE REGISTRATION
Hayden Harper | Operations |  | PARKING + SIGNAGE/PLACE PARKING CONES IN EMPLOYER LOT | OVERSEE LOAD-IN |  | EXHIB. REGISTRATION |  | OVERSEE VOLUNTEERS | ALL REGISTRATION BOOTHS OPEN | PARKING/CONE CHECK | ON-SITE REGISTRATION |  | OPENING CEREMONY | ON-SITE REGISTRATION |  | BREAK/MEET W/ EMPLOYER |  | OVERSEE VOLUNTEERS/FLOAT |  | OVERSEE PARKING |  |  | COLLECT CONES + SIGNAGE
Mia Husty | Operations |  |  | STUDENT REGISTRATION/BADGES |  | OVERSEE REGISTRATION/BADGES |  | EXHIBITOR ITEMS TO BOOTHS | ALL REGISTRATION BOOTHS OPEN | PARKING/CONE CHECK | STUDENT REGISTRATION |  | OPENING CEREMONY | STUDENT REGISTRATION |  |  | CROWD CONTROL/FLOAT | BREAK/ MEET W/ EMPLOYER
Lily Hong | Operations |  | INTERIOR SIGNAGE | OVERSEE LOAD-IN |  | EXHIB. REGISTRATION |  |  | ALL REGISTRATION BOOTHS OPEN | EXHIBITOR RUNNER | ON-SITE REGISTRATION/OVERSEE EXHIB. |  | OPENING CEREMONY | STUDENT REGISTRATION |  |  | ON-SITE REGISTRATION | BREAK/ MEET W/ EMPLOYER |  | OVERSEE CROWD CONTROL/FLOAT |  |  | COLLECT INTERIOR SIGNAGE
Hayeon Kim | Operations |  |  | STUDENT REGISTRATION/BADGES |  | OVERSEE REGISTRATION/BADGES |  | OVERSEE VOLUNTEERS | ALL REGISTRATION BOOTHS OPEN | EXHIBITOR RUNNER | STUDENT REGISTRATION |  | OPENING CEREMONY | BREAK/MEET W/ EMPLOYER |  | STUDENT REGISTRATION | CROWD CONTROL/FLOAT | OVERSEE VOLUNTEERS/FLOAT
Deja-Ray Mason | Training/Development Lead | ARRIVE + CHECK IN | ASSIST OPS IN REGISTRATION |  | OVERSEE/FLOAT | REGISTRATION SETUP |  | ASSIST VOLUNTEER LEAD & COLEAD | PLACE TWO WATER BOTTLES ON EACH EMPLOYER TABLE | CHECK ALL BOOTH QR CODES | DIRECT VOLUNTEERS TO ASSIST EMPLOYERS | OVERSEE/FLOAT | OPENING CEREMONY | CHECK-IN EMPLOYERS |  | OVERSEE VOLUNTEERS | BREAK/ MEET W/ EMPLOYER |  | OVERSEE VOLUNTEERS | FLOAT |  |  | ASSIST W/BREAKDOWN
Logan Lyon | Training/Development Co-Lead |  | ASSIST OPS IN REGISTRATION | BRING VOLUNTEER ITEMS TO FLOOR |  | CHECK IN EARLY VOLUNTEERS | VOLUNTEER MANAGEMENT/ MONITORING CHAT LINE |  |  |  | DIRECT VOLUNTEERS TO ASSIST EMPLOYERS |  | OPENING CEREMONY | BREAK/ MEET W/ EMPLOYER |  | CHECK IN EMPLOYERS | OVERSEE/ FLOAT | CHECK IN EMPLOYERS/VOLUNTEERS |  |  |  |  | ASSIST W/BREAKDOWN
Sera Singleton | Training/Development |  | BRING EMPLOYER/SPONSOR ITEMS TO FLOOR |  | SET OUT EMPLOYER GIFTS | OVERSEE/FLOAT | ASSIST BREAKFAST SETUP | CHECK IN VOLUNTEERS/ASSIST VOLUNTEER MANAGER | CHECK IN EMPLOYERS | MONITOR CHATS | OVERSEE/FLOAT | ASSIST WITH VOLUNTEER CHECK IN/ CHECK OUT | OPENING CEREMONY | MONITOR CHATS | FLOATS | BREAK/MEET W/ EMPLOYER |  | FLOAT | CHECK IN EMPLOYERS |  |  |  | ASSIST W/BREAKDOWN
Elliana Ortiz | Training/Development |  | BRING EMPLOYER/SPONSOR ITEMS TO FLOOR |  | SET OUT EMPLOYER GIFTS | MONITOR CHATS | ASSIST BREAKFAST SETUP |  | CHECK IN EMPLOYERS | CHECK ALL BOOTH QR CODES | OVERSEE/FLOAT | MONITOR CHATS | OPENING CEREMONY | CHECK-IN EMPLOYERS | BREAK/MEET WITH EMPLOYER |  | CHECK IN EMPLOYERS | MONITOR CHAT/ FLOAT | CHECK IN EMPLOYERS |  |  |  | ASSIST W/BREAKDOWN
Amelia Patane | Training Development |  | SET UP VOLUNTEER CHECK-IN | BRING VOLUNTEER ITEMS TO FLOOR |  | OVERSEE/FLOAT | VOLUNTEER MANAGEMENT/ MONITORING CHAT LINE |  | PLACE TWO WATER BOTTLES ON EACH EMPLOYER TABLE | VOLUNTEER MANAGEMENT/ MONITORING CHAT LINE | CHECK OUT VOLUNTEERS/ASSIST VOLUNTEER LEAD |  | OPENING CEREMONY | VOLUNTEERS |  | MONITOR CHATS | VOLUNTEER CHECK IN | BREAK/MEET W/ EMPLOYER |  | VOLUNTEER MANAGEMENT |  |  | ASSIST W/BREAKDOWN
Alex Trevino | Sales/Development Lead | ARRIVE + CHECK IN | ASSIST OTHER DEPARTMENTS WITH SET UP | [8 empty] | GREET/THANK SPONSORS | OPENING CEREMONY | SPONSOR RECRUITMENT |  | BREAK |  | SPONSOR RECRUITMENT |  |  |  |  | ASSIST W/BREAKDOWN
Lauren Muermann | Sales Development Co-Lead | [11 empty] | OPENING CEREMONY | SPONSOR RECRUITMENT |  |  |  | BREAK |  | SPONSOR RECRUITMENT |  |  | ASSIST W/BREAKDOWN
Olivia Townsend | Procurement Lead | ARRIVE + CHECK IN | CLOSET MANAGEMENT |  |  | FLOATER/CRISIS MANAGEMENT | [6 empty] | OPENING CEREMONY | FLOATER |  | MEET WITH EMPLOYERS | FLOATER | FLOATER |  |  |  |  | ASSIST W/BREAKDOWN
JoHannah Sill | Procurement Co-Lead | [11 empty] | OPENING CEREMONY |  |  | FLOATER | MEET WITH EMPLOYERS

## OPS SCHEDULES
ISABELA IRIZARRY |  | JUSTINA RUIZ |  | HAYDEN HARPER |  | MIA HUSTY |  | LILY HONG |  | HA YEON KIM
SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE
5:00 | ARRIVAL + CHECK IN | 5:00 | ARRIVAL + CHECK IN | 5:00 | ARRIVAL + CHECK IN | 5:00 | ARRIVAL + CHECK IN | 5:00 | ARRIVAL + CHECK IN | 5:00 | ARRIVAL + CHECK IN
5:10 | COLLECT BADGES + INV | 5:10 | COLLECT BADGES + INV | 5:10 | PLACE PARKING + SIGNAGE/PLACE PARKING CONES IN EMPLOYER LOT | 5:10 | PLACE PARKING + SIGNAGE/PLACE PARKING CONES IN EMPLOYER LOT | 5:10 | PLACE INTERIOR SIGNAGE | 5:10 | PLACE INTERIOR SIGNAGE
5:30 | REGISTRATION SET-UP | 5:30 | OVERSEE LOAD-IN | 5:30 | OVERSEE LOAD-IN | 5:30 | REGISTRATION SET-UP | 5:30 | OVERSEE LOAD-IN | 5:30 | REGISTRATION SET-UP
6:00 |  | 6:00 |  | 6:00 |  | 6:00 |  | 6:00 |  | 6:00
6:30 | OVERSEE REG./BADGES | 6:30 | EXHIBITOR REGISTRATION | 6:30 | EXHIBITOR REGISTRATION | 6:30 | OVERSEE REGISTRATION | 6:30 | EXHIBITOR REGISTRATION | 6:30 | OVERSEE REGISTRATION
7:00 |  | 7:00 |  | 7:00 |  | 7:00 |  | 7:00 |  | 7:00
7:30 | WALKTHROUGH W/ FREEMAN | 7:30 | WALKTHROUGH W/ FREEMAN | 7:30 | OVERSEE VOLUNTEERS | 7:30 | EXHIBITOR ITEMS 2 BOOTHS | 7:30 | EXHIBITOR ITEMS 2 BOOTHS | 7:30 | OVERSEE VOLUNTEERS
8:00 | ALL REGISTRATION BOOTHS OPEN | 8:00 | ALL REGISTRATION BOOTHS OPEN | 8:00 | ALL REGISTRATION BOOTHS OPEN | 8:00 | ALL REGISTRATION BOOTHS OPEN | 8:00 | ALL REGISTRATION BOOTHS OPEN | 8:00 | ALL REGISTRATION BOOTHS OPEN
8:30 | FINALIZE STUDENT REG. | 8:30 | FINALIZE STUDENT REG. | 8:30 | PARKING CONE CHECK | 8:30 | PARKING CONE CHECK | 8:30 | EXHIBITOR RUNNER | 8:30 | EXHIBITOR RUNNER
9:00 | STUDENT REGISTRATION | 9:00 | ON-SIGHT REG./ OVERSEE EXHIB. | 9:00 | ON-SIGHT REGISTRATION | 9:00 | STUDENT REGISTRATION | 9:00 | ON-SIGHT REG./OVERSEE EXHIBITORS | 9:00 | STUDENT REGISTRATION
9:30 |  | 9:30 |  | 9:30 |  | 9:30 |  | 9:30 |  | 9:30
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | FIRE MARSHALL VISIT | 10:30 | ON-SIGHT REGISTRATION | 10:30 | ON-SIGHT REGISTRATION | 10:30 | STUDENT REGISTRATION | 10:30 | STUDENT REGISTRATION | 10:30 | BREAK/MEET W/ EMPLOYERS
11:00 | BREAK/MEET W/ EMPLOYERS | 11:00 |  | 11:00 |  | 11:00 |  | 11:00 |  | 11:00
11:30 |  | 11:30 |  | 11:30 | BREAK/MEET W/ EMPLOYERS | 11:30 |  | 11:30 |  | 11:30 | STUDENT REGISTRATION
12:00 | OVERSEE REG/FLOAT | 12:00 | BREAK/MEET W/ EMPLOYERS | 12:00 |  | 12:00 | CROWD CONTROL/FLOAT | 12:00 | ON-SIGHT REGISTRATION | 12:00
12:30 |  | 12:30 |  | 12:30 | OVERSEE VOLUNTEERS/FLOAT | 12:30 | BREAK/ MEET W/ EMPLOYERS | 12:30 | BREAK/MEET W/ EMPLOYERS | 12:30
13:00 |  | 13:00 | OVERSEE REG/FLOAT | 13:00 |  | 13:00 |  | 13:00 | OVERSEE CROWD CONTROL/FLOAT | 13:00 | OVERSEE CROWD CONTROL/FLOAT
13:30 |  | 13:30 |  | 13:30 | OVERSEE PARKING | 13:30 | OVERSEE PARKING | 13:30 |  | 13:30
14:00 | CLASS PHOTO & BREAK | 14:00 | CLASS PHOTO & BREAK | 14:00 | CLASS PHOTO & BREAK | 14:00 | CLASS PHOTO & BREAK | 14:00 | CLASS PHOTO & BREAK | 14:00 | CLASS PHOTO & BREAK
14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30
15:00 | REGISTRATION BREAKDOWN | 15:00 | REGISTRATION BREAKDOWN | 15:00 | COLLECT CONES + SIGNAGE | 15:00 | COLLECT CONES + SIGNAGE | 15:00 | INTERIOR SIGNAGE BREAKDOWN | 15:00 | INTERIOR SIGNAGE BREAKDOWN
15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30
16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED

## MARKETING SCHEDULES
DRAKE SPENO |  | MERELIN ALMONTE |  | CATE DAUGHTERY |  | AMY HELGESON |  | KILEY MCDERMOTT |  | DARIA ALVARADO SOLER
SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE
5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN
5:10 | ASSIST WITH SET UP | 5:10 | ASSIST WITH SET UP | 5:10 | ASSIST WITH SET UP | 5:10 | ASSIST WITH SET UP | 5:10 | ASSIST WITH SET UP | 5:10 | ASSIST WITH SET UP
5:30 |  | 5:30 |  | 5:30 |  | 5:30 |  | 5:30 |  | 5:30
6:00 |  | 6:00 |  | 6:00 |  | 6:00 |  | 6:00 |  | 6:00
6:30 |  | 6:30 |  | 6:30 |  | 6:30 |  | 6:30 |  | 6:30
7:00 |  | 7:00 |  | 7:00 |  | 7:00 |  | 7:00 |  | 7:00
7:30 |  | 7:30 |  | 7:30 |  | 7:30 |  | 7:30 |  | 7:30
8:00 |  | 8:00 |  | 8:00 |  | 8:00 |  | 8:00 |  | 8:00
8:30 | FILM PRE-EVENT REELS | 8:30 | CONTINUE ASSISTING w/ SET UP | 8:30 | FILM PRE-EVENT REELS | 8:30 | CONTINUE ASSISTING w/ SET UP | 8:30 | FILM PRE-EVENT REELS | 8:30 | FILM PRE-EVENT REELS
9:00 | FLOAT/CORDINATE CONTENT/ASSIST KNIGHTRO | 9:00 | FLOAT/ASSIST STAFF | 9:00 | CORDINATE WITH STAFF | 9:00 | ASSIST WITH VOLUNTEERS | 9:00 | KNIGHTRO ATTENDANT | 9:00 | ASSIST WITH VOLUNTEERS
9:30 |  | 9:30 |  | 9:30 |  | 9:30 |  | 9:30 |  | 9:30
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | FILM/TAKE CONTENT | 10:30 | CHECK IN W/ VOLUNTEERS | 10:30 | CHECK IN W/ VOLUNTEERS | 10:30 | TAKE PROFESSIONAL PHOTOS | 10:30 | FILM/TAKE CONTENT | 10:30 | KNIGHTRO ATTENDANT
11:00 | CAREER FAIR LEGACY WALL/FILM | 11:00 | BREAK/ MEET W/ EMPLOYERS | 11:00 | BREAK/ MEET W/ EMPLOYERS | 11:00 | CAREER FAIR LEGACY WALL | 11:00 | CAREER FAIR LEGACY WALL | 11:00 | CAREER FAIR LEGACY WALL
11:30 | SOCIAL MEDIA | 11:30 |  | 11:30 |  | 11:30 | TAKE PROFESSIONAL PHOTOS | 11:30 | SURVEY/COLLECT BADGES | 11:30 | FILM CONTENT
12:00 | BREAK/ MEET W/ EMPLOYERS | 12:00 | SURVEY/COLLECT BADGES | 12:00 | SOCIAL MEDIA | 12:00 | CHARGE CAMERA/SOCIAL MEDIA | 12:00 | CHECK IN w/ VOLUNTEERS | 12:00 | BREAK/ MEET W/ EMPLOYERS
12:30 |  | 12:30 |  | 12:30 |  | 12:30 | CHECK IN ON PHOTO BOOTH | 12:30 | CHECK IN ON PHOTO BOOTH | 12:30
13:00 | FILM/TAKE CONTENT | 13:00 | SOCIAL MEDIA | 13:00 | CHECK IN ON PHOTO BOOTH | 13:00 | BREAK/MEET WITH EMPLOYERS | 13:00 | BREAK/ MEET W/ EMPLOYERS | 13:00 | CHECK IN W/ VOLUNTEERS
13:30 | SOCIAL MEDIA | 13:30 |  | 13:30 | FILM VLOG | 13:30 |  | 13:30 |  | 13:30 | SURVEY/COLLECT BADGES
14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK
14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30
15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN
15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30
16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED

## DECOR SCHEDULES
ALEXIS JONES |  | BIANKA MEJIA |  | ADAM HOLBROOK |  | EMILY STRICKLAND |  | TAMARA HOEFINGER |  | ASHLYN STRAUGHN
SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE
5:00 | ARRIVING & CHECK-IN | 5:00 | ARRIVING & CHECK-IN | 5:00 | ARRIVING & CHECK-IN | 5:00 | ARRIVING & CHECK-IN | 5:00 | ARRIVING & CHECK-IN | 5:00 | ARRIVING & CHECK-IN
5:10 | WORKING ON FRONT ENTRANCE | 5:10 | WORKING ON FRONT ENTRANCE | 5:10 | WORKING ON FRONT ENTRANCE | 5:10 | WORKING ON FRONT ENTRANCE | 5:10 | WORKING ON FRONT ENTRANCE | 5:10 | WORKING ON FRONT ENTRANCE
5:30 |  | 5:30 |  | 5:30 |  | 5:30 |  | 5:30 |  | 5:30
6:00 |  | 6:00 |  | 6:00 |  | 6:00 |  | 6:00 |  | 6:00
6:30 | ASSIST WITH BREAKFAST SET UP | 6:30 | ASSIST WITH BREAKFAST SET UP | 6:30 | ASSIST WITH BREAKFAST SET UP | 6:30 | ASSIST W/ BREAKFAST SETUP | 6:30 | ASSIST WITH BREAKFAST SET UP | 6:30 | ASSIST WITH BREAKFAST SET UP
7:00 |  | 7:00 |  | 7:00 |  | 7:00 |  | 7:00 |  | 7:00
7:30 | SET UP REGISTRATION TABLES | 7:30 | SET UP PATIO | 7:30 |  | 7:30 | SET UP GAZEBO AND RESTROOMS | 7:30 | SET UP GAZEBO AND RESTROOMS | 7:30
8:00 |  | 8:00 |  | 8:00 | FINAL TOUCHES ON RELAXATION ROOM | 8:00 |  | 8:00 |  | 8:00 | HELP WITH RELAXATION ROOM
8:30 | ASSIST W/REGISTRATION | 8:30 | OVERSEE EMPLOYER USHERS | 8:30 | SET UP DRINKING STATION/STAND BY | 8:30 | SET UP DRINKING STATION/STAND BY | 8:30 | SET UP DRINKING STATION/STAND BY | 8:30 | SET UP DRINKING STATION/STAND BY
9:00 |  | 9:00 |  | 9:00 | EMPLOYER USHER | 9:00 | EMPLOYER USHER | 9:00 | EMPLOYER USHER | 9:00 | EMPLOYER USHER
9:30 | CHECK IN EMPLOYERS | 9:30 | CHECK IN EMPLOYERS | 9:30 | CHECK IN EMPLOYERS | 9:30 | BREAKDOWN BREAKFAST | 9:30 | BREAKDOWN BREAKFAST | 9:30 | CHECK IN EMPLOYERS
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | SURVEY/COLLECT BADGES | 10:30 | BREAK/ MEET W/ EMPLOYER | 10:30 | BREAKDOWN BREAKFAST | 10:30 | BREAKDOWN BREAKFAST | 10:30 | BREAKDOWN BREAKFAST | 10:30 | BREAKDOWN BREAKFAST
11:00 |  | 11:00 |  | 11:00 |  | 11:00 | SET UP LUNCH | 11:00 | SET UP LUNCH | 11:00 | MONITOR R&R ROOM
11:30 | BREAK/ MEET W/ EMPLOYER | 11:30 | SURVEY/COLLECT BADGES | 11:30 | OVERSEE EMPLOYEE DINING | 11:30 | FLOATING | 11:30 | MONITOR R&R ROOM | 11:30 | SURVEY/COLLECT BADGES
12:00 |  | 12:00 | OVERSEE EMPLOYEE DINING | 12:00 |  | 12:00 | BREAK/ MEET W/ EMPLOYER | 12:00 | SURVEY/COLLECT BADGES | 12:00 | OVERSEE EMPLOYEE DINING
12:30 | MONITOR R&R ROOM | 12:30 | FLOATING | 12:30 | SURVEY/COLLECT BADGES | 12:30 |  | 12:30 | FLOATING | 12:30 | BREAK/ MEET W/ EMPLOYER
13:00 | FLOATING | 13:00 | OVERSEE EMPLOYEE DINING | 13:00 | MONITOR R&R ROOM | 13:00 | SURVEYS/COLLECTING BADGES | 13:00 | SURVEY/COLLECT BADGES | 13:00
13:30 | FLOATING | 13:30 | SURVEYS/COLLECTING BADGES | 13:30 | BREAKDOWN LUNCH | 13:30 | BREAKDOWN LUNCH | 13:30 | BREAKDOWN LUNCH | 13:30 | SURVEYS/COLLECTING BADGES
14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK
14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30
15:00 | ASSIST W/BREAKDOWN | 15:00 | ASSIST W/BREAKDOWN | 15:00 | ASSIST W/BREAKDOWN | 15:00 | ASSIST W/BREAKDOWN | 15:00 | ASSIST W/BREAKDOWN | 15:00 | ASSIST W/BREAKDOWN
15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30
16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED

## T&D SCHEDULES
DEJA-RAY MASON |  | LOGAN LYON |  | SERA SINGLETON |  | ELLIANA ORTIZ |  | AMELIA PATANE
SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE |  | SCHEDULE
5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN
5:10 | ASSIST OPS IN REGISTRATION | 5:10 | ASSIST OPS IN REGISTRATION | 5:10 | BRING EMPLOYER/SPONSOR ITEMS TO FLOOR | 5:10 | BRING EMPLOYER/SPONSOR ITEMS TO FLOOR | 5:10 | SET UP VOLUNTEER CHECK-IN
5:30 |  | 5:30 | BRING VOLUNTEER ITEMS TO FLOOR | 5:30 |  | 5:30 |  | 5:30 | BRING VOLUNTEER ITEMS TO FLOOR
6:00 | OVERSEE/FLOAT | 6:00 |  | 6:00 | SET OUT EMPLOYER GIFTS | 6:00 | SET OUT EMPLOYER GIFTS | 6:00
6:30 | REGISTRATION SETUP | 6:30 | CHECK IN EARLY VOLUNTEERS | 6:30 | OVERSEE/ FLOAT | 6:30 | MONITOR CHATS | 6:30 | OVERSEE/FLOAT
7:00 |  | 7:00 | VOLUNTEER MANAGEMENT/ MONITORING CHAT LINE | 7:00 | ASSIST BREAKFAST SETUP | 7:00 | ASSIST BREAKFAST SETUP | 7:00 | VOLUNTEER MANAGEMENT/ MONITORING CHAT LINE
7:30 | ASSIST VOLUNTEER LEAD & CO-LEAD | 7:30 |  | 7:30 | CHECK IN VOLUNTEERS/ASSIST VOLUNTEER MANAGER | 7:30 |  | 7:30
8:00 | PLACE TWO WATER BOTTLES ON EACH EMPLOYER TABLE | 8:00 |  | 8:00 | CHECK IN EMPLOYERS | 8:00 | CHECK IN EMPLOYERS | 8:00 | PLACE TWO WATER BOTTLES ON EACH EMPLOYER TABLE
8:30 | CHECK ALL BOOTH QR CODES | 8:30 |  | 8:30 | MONITOR CHATS | 8:30 | CHECK ALL BOOTH QR CODES | 8:30 | VOLUNTEER MANAGEMENT/ MONITORING CHAT LINE
9:00 | DIRECT VOLUNTEERS TO ASSIST EMPLOYERS | 9:00 | DIRECT VOLUNTEERS TO ASSIST EMPLOYERS | 9:00 | OVERSEE/ FLOAT | 9:00 | OVERSEE/FLOAT | 9:00 | CHECK OUT VOLUNTEERS/ASSIST VOLUNTEER LEAD
9:30 | OVERSEE/FLOAT | 9:30 |  | 9:30 | ASSIST WITH VOLUNTEER CHECK IN/ CHECK OUT | 9:30 | MONITOR CHATS | 9:30
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | CHECK-IN EMPLOYERS | 10:30 | BREAK/MEET W/ EMPLOYERS | 10:30 | MONITOR CHATS | 10:30 | CHECK-IN EMPLOYERS | 10:30 | VOLUNTEERS
11:00 |  | 11:00 |  | 11:00 | FLOAT | 11:00 | BREAK/MEET W/ EMPLOYERS | 11:00
11:30 | OVERSEE VOLUNTEERS | 11:30 | CHECK IN EMPLOYERS | 11:30 | BREAK/MEET W/ EMPLOYERS | 11:30 |  | 11:30 | MONITOR CHATS
12:00 | BREAK/MEET W/ EMPLOYERS | 12:00 | OVERSEE/ FLOAT | 12:00 |  | 12:00 | CHECK IN EMPLOYERS | 12:00 | VOLUNTEER CHECK IN
12:30 |  | 12:30 | CHECK IN EMPLOYERS/ VOLUNTEERS | 12:30 | FLOAT | 12:30 | MONITOR CHAT/ FLOAT | 12:30 | BREAK/MEET W/ EMPLOYERS
13:00 | OVERSEE VOLUNTEERS | 13:00 |  | 13:00 | CHECK IN EMPLOYERS | 13:00 | CHECK IN EMPLOYERS | 13:00
13:30 | FLOAT | 13:30 |  | 13:30 |  | 13:30 |  | 13:30 | VOLUNTEER MANAGEMENT
14:00 | CLASS PHOTO & LUNCH BREAK | 14:00 | CLASS PHOTO & LUNCH BREAK | 14:00 | CLASS PHOTO & LUNCH BREAK | 14:00 | CLASS PHOTO & LUNCH BREAK | 14:00 | CLASS PHOTO & LUNCH BREAK
14:30 |  | 14:30 |  | 14:30 |  | 14:30 |  | 14:30
15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN | 15:00 | ASSIST W/ BREAKDOWN
15:30 |  | 15:30 |  | 15:30 |  | 15:30 |  | 15:30
16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED

## S&D SCHEDULES
ALEX TREVINO |  | LAUREN MUERMANN
SCHEDULE |  | SCHEDULE
5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN
5:10 | ASSIST WITH SETUP | 5:10 | ASSIST WITH SETUP
5:30 |  | 5:30
6:00 |  | 6:00
6:30 |  | 6:30
7:00 |  | 7:00
7:30 |  | 7:30
8:00 |  | 8:00
8:30 |  | 8:30
9:00 |  | 9:00
9:30 | GREET/THANK SPONSORS | 9:30 | GREET/THANK SPONSORS
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | SPONSOR RECRUITMENT | 10:30 | SPONSOR RECRUITMENT
11:00 |  | 11:00
11:30 | BREAK/MEET WITH EMPLOYERS | 11:30
12:00 |  | 12:00
12:30 | SPONSOR RECRUITMENT | 12:30 | BREAK/MEET WITH EMPLOYERS
13:00 |  | 13:00
13:30 |  | 13:30 | SPONSOR RECRUITMENT
14:00 | LUNCH BREAK | 14:00 | LUNCH BREAK
14:30 |  | 14:30
15:00 | ASSIST WITH BREAKDOWN | 15:00 | ASSIST WITH BREAKDOWN
15:30 |  | 15:30
16:00 | DONE | 16:00 | DONE

## PROCUREMENT SCHEDULES
OLIVIA TOWNSEND |  | JOHANNAH SILL
SCHEDULE |  | SCHEDULE
5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN
5:10 | CLOSET MANAGEMENT | 5:10 | CLOSET MANAGEMENT
5:30 |  | 5:30
6:00 |  | 6:00
6:30 |  | 6:30
7:00 | FLOATER/CRISIS MANAGEMENT | 7:00 | FLOATER/CRISIS MANAGEMENT
7:30 |  | 7:30
8:00 |  | 8:00
8:30 |  | 8:30
9:00 |  | 9:00
9:30 |  | 9:30
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | FLOATER | 10:30 | FLOATER
11:00 |  | 11:00
11:30 | MEET WITH EMPLOYERS | 11:30
12:00 | FLOATER | 12:00 | MEET WITH EMPLOYERS
12:30 |  | 12:30 | FLOATER
13:00 |  | 13:00
13:30 |  | 13:30
14:00 | CLASS PHOTO/LUNCH BREAK | 14:00 | CLASS PHOTO/LUNCH BREAK
14:30 |  | 14:30
15:00 | ASSIST WITH BREAKDOWN | 15:00 | ASSIST WITH BREAKDOWN
15:30 |  | 15:30
16:00 | FINISHED | 16:00 | FINISHED

## EXEC SCHEDULES
STEVEN BRINKMAN |  | KAITLIN SMITH |  | HARLEY PAUL
SCHEDULE |  | SCHEDULE |  | SCHEDULE
5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN | 5:00 | ARRIVE + CHECK IN
5:10 | OVERSEE SET UP | 5:10 | OVERSEE SET UP | 5:10 | OVERSEE SET UP
5:30 |  | 5:30 |  | 5:30
6:00 |  | 6:00 |  | 6:00
6:30 |  | 6:30 |  | 6:30
7:00 |  | 7:00 |  | 7:00
7:30 | WALKTHROUGH WITH FREEMAN | 7:30 | WALKTHROUGH WITH FREEMAN | 7:30 | WALKTHROUGH WITH FREEMAN
8:00 |  | 8:00 |  | 8:00
8:30 | OVERSEE/FLOAT | 8:30 | OVERSEE/FLOAT | 8:30 | OVERSEE/FLOAT
9:00 |  | 9:00 |  | 9:00
9:30 |  | 9:30 |  | 9:30
10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY | 10:00 | OPENING CEREMONY
10:30 | FIRE MARSHALL VISIT | 10:30 | FIRE MARSHALL VISIT | 10:30 | FIRE MARSHALL VISIT
11:00 | OVERSEE/FLOAT | 11:00 | OVERSEE/FLOAT | 11:00 | OVERSEE/FLOAT
11:30 |  | 11:30 |  | 11:30
12:00 |  | 12:00 |  | 12:00
12:30 |  | 12:30 |  | 12:30
13:00 |  | 13:00 |  | 13:00
13:30 |  | 13:30 |  | 13:30
14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK | 14:00 | CLASS PHOTO AND LUNCH BREAK
14:30 |  | 14:30 |  | 14:30
15:00 | ASSIST WITH BREAKDOWN | 15:00 | ASSIST WITH BREAKDOWN | 15:00 | ASSIST WITH BREAKDOWN
15:30 |  | 15:30 |  | 15:30
16:00 | FINISHED | 16:00 | FINISHED | 16:00 | FINISHED

## VOLUNTEER SCHEDULES
TIMES | Departments | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00
Set-up (7 - 10) | OPERATIONS | Set-up
Morning (7 -2) | DECOR | Morning
Event (10 - 2) | F&B | [6 empty] | Event
Mid (10 - 4) | TRAINING & DEV | [6 empty] | Mid Shift
Evening (12-4) | MARKETING | [10 empty] | Evening
Whole (7-4) | TEARDOWN/CLEAN UP | Whole Event
Set-up (7 - 10)
Kens Augustin | OPERATIONS | EXHIBITOR REGISTRATION /LOAD IN
Naomi Harper | OPERATIONS | EXHIBITOR REGISTRATION /LOAD IN
Nayshla Rolly | OPERATIONS | EXHIBITOR REGISTRATION /LOAD IN
Rosairy Berroa | OPERATIONS | EXHIBITOR REGISTRATION /LOAD IN
Morning (7 -2)
Sutanya Thomas | OPERATIONS | PARKING | [5 empty] | BREAK | FLOAT/ HELP OPS WHERE NEEDED
Aleena Ridley | TRAINING & DEV | HELP CHECKIN VOLUNTEERS | [6 empty] | BREAK | FLOATING/ SURVEY ATTENDANCE | [5 empty] | Can only volunteer until 1:15
Ariah Claude | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED |  |  |  |  | EXHIBITOR REGISTRATION /LOAD IN |  |  |  | BREAK | STUDENT REGISTRATION
Luis Malone | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED |  |  |  |  | EXHIBITOR REGISTRATION /LOAD IN |  |  |  | BREAK | STUDENT REGISTRATION
Autumn Mantel | TRAINING & DEV | HELP CHECKIN VOLUNTEERS | [6 empty] | BREAK | FLOATING/ SURVEY ATTENDANCE | [5 empty] | Can only volunteer until 1:30
Alyssa Hudson | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED |  |  |  | STUDENT REGISTRATION | [5 empty] | BREAK | FLOAT/ HELP OPS WHERE NEEDED
Whitney Souverain | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED |  |  |  | STUDENT REGISTRATION | [5 empty] | BREAK | FLOAT/ HELP OPS WHERE NEEDED
Kennedy Peyton | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED |  |  |  | STUDENT REGISTRATION | [5 empty] | BREAK | FLOAT/ HELP OPS WHERE NEEDED
Event (10 - 2)
Melanie Hull (Lanie) | TRAINING & DEV | [6 empty] | FLOATING/ SURVEY ATTENDANCE |  | BREAK | FLOATING/ SURVEY ATTENDANCE
Giselle Nardelli | TRAINING & DEV | [6 empty] | FLOATING/ SURVEY ATTENDANCE |  |  | BREAK | FLOATING/ SURVEY ATTENDANCE
Bella West | TRAINING & DEV | [6 empty] | FLOATING/ SURVEY ATTENDANCE |  |  |  | BREAK | FLOATING/ SURVEY ATTENDANCE
Mid (10 - 4)
Olivia Okoskey (Liv) | TRAINING & DEV | [6 empty] | MONITOR DISNEY DINING ROOM DOORS AND TRAFFIC |  |  | BREAK | MONITOR THE CAFE DOORS
Anthony Rodriguez | TRAINING & DEV | [6 empty] | MONITOR DISNEY DINING ROOM DOORS AND TRAFFIC |  |  |  | BREAK | MONITOR THE CAFE DOORS
Katherine Reyes-Wong | TRAINING & DEV | [6 empty] | MONITOR HALL OF FAME |  | BREAK | MONITOR DARDEN AUDITORIUM |  |  |  |  | SURVEY ATTENDANCE | TEARDOWN/CLEAN UP
Izabella Perez (Bella) | TRAINING & DEV | [6 empty] | MONITOR HALL OF FAME |  |  | BREAK | MONITOR DARDEN AUDITORIUM |  |  |  | SURVEY ATTENDANCE | TEARDOWN/CLEAN UP
Valeria Gonzalez | DECOR | [6 empty] | MONITOR THE COURTYARD AND MAINTAIN DECORATIONS |  |  | BREAK | MONITOR THE COURTYARD AND MAINTAIN DECORATIONS |  |  |  | TEARDOWN/CLEAN UP
Amanda Tobin | DECOR | [6 empty] | MONITOR THE COURTYARD AND MAINTAIN DECORATIONS |  |  |  | BREAK | MONITOR THE COURTYARD AND MAINTAIN DECORATIONS |  |  | TEARDOWN/CLEAN UP
Courtney Pierre | OPERATIONS | [6 empty] | STUDENT LOUNGE CLICKER COUNTER |  |  | BREAK | STUDENT LOUNGE CLICKER COUNTER |  |  |  | TEARDOWN/CLEAN UP
Adriel Rosa (AD) | OPERATIONS | [6 empty] | STUDENT LOUNGE CLICKER COUNTER |  |  |  | BREAK | STUDENT LOUNGE CLICKER COUNTER |  |  | TEARDOWN/CLEAN UP
Jeremiah Robinson | TRAINING & DEV | [6 empty] | HELP CHECKIN VOLUNTEERS |  |  |  |  | BREAK | FLOATING/ SURVEY ATTENDANCE |  | TEARDOWN/CLEAN UP
Madeline Forrester (Maddie) | TRAINING & DEV | [6 empty] | HELP CHECKIN VOLUNTEERS |  |  |  |  | BREAK | FLOATING/ SURVEY ATTENDANCE |  | TEARDOWN/CLEAN UP
Rodrigo Orta | DECOR | [6 empty] | MONITOR THE COURTYARD AND MAINTAIN DECORATIONS |  |  |  |  | BREAK | MONITOR THE COURTYARD AND MAINTAIN DECORATIONS |  | TEARDOWN/CLEAN UP
Evening (12-4)
Adrian Milek | TRAINING & DEV | [10 empty] | MONITOR THE CAFE DOORS |  |  |  | TEARDOWN/CLEAN UP
Kate Lambert | TRAINING & DEV | [10 empty] | MONITOR THE CAFE DOORS |  |  |  | TEARDOWN/CLEAN UP
Jacob Molpus | TRAINING & DEV | [10 empty] | FLOAT/ HELP OTHER DEPTS |  |  |  | TEARDOWN/CLEAN UP
Angelina Rodrigiez | TRAINING & DEV | [10 empty] | FLOAT/ HELP OTHER DEPTS |  |  |  | TEARDOWN/CLEAN UP
Nicole Martin Sousa | TRAINING & DEV | [10 empty] | FLOAT/ HELP OTHER DEPTS |  |  |  | TEARDOWN/CLEAN UP
Viney Bharwani | TRAINING & DEV | [10 empty] | FLOAT/ HELP OTHER DEPTS |  |  |  | TEARDOWN/CLEAN UP
Whole (7-4)
Kayla Carrender | F&B | HELP DECORATE THE CAFE |  |  | HELP WITH BREAKFAST |  |  | CLEAN AND PREP FOR LUNCH |  | HELP WITH LUNCH |  | BREAK | HELP WITH LUNCH |  |  | TEARDOWN/CLEAN UP
Kevin Tran | F&B | HELP DECORATE THE CAFE |  |  | HELP WITH BREAKFAST |  |  | CLEAN AND PREP FOR LUNCH |  | HELP WITH LUNCH |  |  | BREAK | HELP WITH LUNCH |  | TEARDOWN/CLEAN UP
Gabriela Valencia Soto (Gaby) | F&B | HELP DECORATE THE CAFE |  |  | HELP WITH BREAKFAST |  |  | CLEAN AND PREP FOR LUNCH |  | HELP WITH LUNCH |  |  |  | BREAK | HELP WITH LUNCH | TEARDOWN/CLEAN UP
Grace Jeffers | F&B | HELP DECORATE THE CAFE |  |  | HELP WITH BREAKFAST |  |  | CLEAN AND PREP FOR LUNCH |  | HELP WITH LUNCH | BREAK | HELP WITH LUNCH |  |  |  | TEARDOWN/CLEAN UP
Dylan Webb | OPERATIONS | PARKING | [5 empty] | BREAK | FLOAT/ HELP OPS WHERE NEEDED | [6 empty] | TEARDOWN/CLEAN UP
Abigail Fooshee (Abby) | OPERATIONS | PARKING | [6 empty] | BREAK | FLOAT/ HELP OPS WHERE NEEDED | [5 empty] | TEARDOWN/CLEAN UP
Natalie Weiss | OPERATIONS | EXHIBITOR REGISTRATION/ LOAD IN |  |  |  |  | EXHIBITOR REGISTRATION /LOAD IN |  |  |  | BREAK | STUDENT REGISTRATION |  |  |  | TEARDOWN/CLEAN UP
Florrie Sie | DECOR | HELP DECOR WHERE NEEDED |  |  |  |  | MONITOR THE READY AND RELAXATION ROOM |  |  |  | BREAK | MONITOR THE HEADSHOT ROOM |  |  |  | TEARDOWN/CLEAN UP
Kylie Hartwell | DECOR | HELP DECOR WHERE NEEDED |  |  |  |  | MONITOR THE READY AND RELAXATION ROOM |  |  |  |  | BREAK | MONITOR THE HEADSHOT ROOM |  |  | TEARDOWN/CLEAN UP
Jasmine Nava | DECOR | HELP DECOR WHERE NEEDED |  |  |  |  | MONITOR THE HEADSHOT ROOM |  |  |  | BREAK | MONITOR THE READY AND RELAXATION ROOM |  |  |  | TEARDOWN/CLEAN UP
Kaitlyn Jadevaia | DECOR | HELP DECOR WHERE NEEDED |  |  |  |  | MONITOR THE HEADSHOT ROOM |  |  |  |  | BREAK | MONITOR THE READY AND RELAXATION ROOM |  |  | TEARDOWN/CLEAN UP
Isabelle Nazario | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED | [5 empty] | BREAK | PARKING | [6 empty] | TEARDOWN/CLEAN UP
Viviana Pena | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED | [6 empty] | BREAK | PARKING | [5 empty] | TEARDOWN/CLEAN UP
Saniya Henderson (Niya) | OPERATIONS | FLOAT/ HELP OPS WHERE NEEDED | [5 empty] | BREAK | PARKING | [6 empty] | TEARDOWN/CLEAN UP
Brielle McDowell | MARKETING | TAKE PHOTOS AND GET CONTENT | [7 empty] | BREAK | TAKE PHOTOS AND GET CONTENT |  |  |  |  | TEARDOWN/CLEAN UP
Francis Pepe (Frankie) | MARKETING | TAKE PHOTOS AND GET CONTENT | [8 empty] | BREAK | TAKE PHOTOS AND GET CONTENT |  |  |  | TEARDOWN/CLEAN UP
Isabel Tobias | MARKETING | TAKE PHOTOS AND GET CONTENT | [6 empty] | BREAK | TAKE PHOTOS AND GET CONTENT | [5 empty] | TEARDOWN/CLEAN UP
Skyla Mejias (Sky) | TRAINING & DEV | FLOAT/ HELP OTHER DEPTS |  |  |  | MONITOR THE CAFE DOORS |  |  |  |  | BREAK | MONITOR DISNEY DINING ROOM DOORS AND TRAFFIC |  |  |  | SURVEY ATTENDANCE | TEARDOWN/CLEAN UP
Olivia Bergler | TRAINING & DEV | FLOAT/ HELP OTHER DEPTS |  |  |  | MONITOR THE CAFE DOORS | [5 empty] | BREAK | MONITOR DISNEY DINING ROOM DOORS AND TRAFFIC |  |  | SURVEY ATTENDANCE | TEARDOWN/CLEAN UP
Matthew Brewer (Matt) | TRAINING & DEV | FLOAT/ HELP OTHER DEPTS |  |  |  | MONITOR THE DARDEN AUDITORIUM DOORS |  |  |  |  | BREAK | MONITOR HALL OF FAME |  |  |  | SURVEY ATTENDANCE | TEARDOWN/CLEAN UP
Sydney Rucys | TRAINING & DEV | FLOAT/ HELP OTHER DEPTS |  |  |  | MONITOR THE DARDEN AUDITORIUM DOORS | [5 empty] | BREAK | MONITOR HALL OF FAME |  |  | SURVEY ATTENDANCE | TEARDOWN/CLEAN UP